## Tasks
Module | Sub Modules | Start Date | End Date | Status | Optional Concepts
Git Repository | Creating GIT Repo | 2017-03-14 |  | Completed
| Check-in Initial Code |  | 2017-03-15 | Completed
Data Model Creation | items.xml | 2017-03-16 |  | Completed
| Essential Data |  | 2017-03-17 | Completed
Data Loading | Hot Folder | 2017-03-20 | 2017-03-22 | Completed | Data Hub
hMC Customization | adhigas tab in hMC
Storefront | WCMS - Homepage
CSS integration
Product Cockpit(PCM) | Users Creation
User Roles/AccessRights
PCM Customization
Synchronization
Workflows - 2 atleast
Account Management | Registration
Login

## Data Model
PARENT MODEL | HYBRIS MODEL | MERCH ATTRIBUTE | DATA TYPE | New/OOTB | DESCRIPTION | SAMPLE VALUE | READ-ONLY | ESSENTIAL | SEARCHABLE | FACET/FILTER | ADDITIONAL COMMENTS
Product | AdighaProduct | Recipe | Recipe | New
|  | isTodaySpecial | Boolean | New
VariantProduct | AdighaVariantProduct | Size | String | New |  | Medium/Large/Small | Y | Y | N | N
|  | Type | String | New |  | Cheese/NoCheese | Y | Y | N | N

## Recipe
PARENT MODEL | HYBRIS MODEL | MERCH ATTRIBUTE | DATA TYPE | New/OOTB | DESCRIPTION | SAMPLE VALUE | READ-ONLY | ESSENTIAL | SEARCHABLE | FACET/FILTER | ADDITIONAL COMMENTS
| AdighaRecipe | Code | String | New
|  | Name | String | New
|  | Description | String | New
|  | Attachment | CLOB/BLOB | New